## Introduction
Grey Fleet Toolkit: Part 6
Travel Action Plan
A Travel Action Plan complements wider policy documents such as a Travel Policy. The Action Plan is a brief and specific document that sets out and sets out specific agreed tasks as a SMART (specific, measurable, agreed upon, realistic and time focused) targets. This template sets out an example Travel Action Plan formed of two tabs: a template setting out what might be included and areas to focus on, and a completed example taken from a real Travel Action Plan to act as a guide.
In order to use the Action Plan the following procedure is helpful: - Produce Travel Policy based on the ambitions of the organisation - Prioritise activities based on the desires , drivers and aspirations of the organisation - Establish a timeframe (suggest 2 years max) and set out what can be realistically achieved in this period - Discuss and agree funding / resources for these actions - Set out draft travel Action Plan including the above prioritised actions, timeframes and funding - Seek agreement to Actions - Deliver, assess and review. Repeat process at end of defined timeframe (E.g. 2 years)

## Template
Travel Action Plan Template
ACTION | ANNUAL COST | BUDGET | OWNER | TIMESCALE | COMMENTS | CHANGES SINCE PREVIOUS PLAN AND COMMENTS
Headline of the activity e.g: baselining, communication | This may be a £ cost or in kind officer time | May be a corporate or divisional, department budget e.g: Sustainability, H&S | The sponsor or responsbile officer for this task | This should be a SMART timeframe | Used to set out what the action is in more detailed terms and linked to the Travel Policy. | This should set out the last iteration of the policy and deviations and changes from it.
Active Travel
|  | Titles such as 'Active Travel' are example titles |  |  | The dividers separate indidual sections
Company Car Lease Scheme
Improving Staff Information and Raising Awareness
It should be noted that whilst the majority of resource implications set out above are for officer time, this carries with it a cost that must be accounted for.

## Completed
Completed Travel Action Plan
ACTION | ANNUAL COST | BUDGET | OWNER | TIMESCALE | COMMENTS | CHANGES SINCE PREVIOUS PLAN AND COMMENTS
Grey Fleet Solution
Benchmark existing fleet | Officer Time | Corporate | Initiator | To be agreed | Assessment of Grey Fleet options | For Completion on a site by site basis
Baselining exercise | Officer Time | Corporate |  | To be agreed | Assessment of Current Operation and Usage | For Completion on a site by site basis
Report to Board | Officer Time | Corporate | Initiator | To be agreed | Decision Makers Agreement of solution | For Completion on a site by site basis
Gain scheme Buy-in | Officer Time | Corporate |  | To be agreed | Communication with Stakeholders (inc unions, employee reps, members, senior officers) | For Completion on a site by site basis
OJEU Compliant Procurement | Officer Time | Corporate | Initiator and Procurement Dept | To be agreed | Tender and Procurement of Solution | For Completion on a site by site basis
Commissioning and Operation | Officer Time | Corporate | Initiator, HR | To be agreed | Initiation, Commissioning and Operation of Solution | For Completion on a site by site basis
Review of Car Scheme Success | Officer Time | Corporate | Initiator/Audit | To be agreed | Financial Review of the project from inception to end of first year (Benefits Realisation) | For Completion on a site by site basis
Removal of all historic Essential, Casual and Lease allowances | Officer Time | Corporate | Initiator | To be agreed | Scheme set up to save agreed figure(£) per year, take control of risk and fleet, reduce emissions and congestion and remove all allowances. | For Completion on a site by site basis
Active Travel
Cycling | Officer Time | Corporate | Initiator | To be agreed | Ensure that shower facilities, secure bike racks and lockers for helmets and equipment are in place as well as areas for drying clothes. Consider milage payment | Monitor through staff surveys
Walking | Officer Time | Corporate | Initiator | To be agreed | Ensure that this is encouraged | Monitor through staff surveys
Company Car Lease Scheme
Review Mileage and claims data | Officer time | Corporate | Initiator | To be Agreed | Benchmark and review of data collected from Leasee Car users and submitted to Internal Audit | For Completion on a site by site basis
Consult with affected staff | Officer time | Corporate | Initiator | To be Agreed | Meet with specific staff to set out issues and discuss and agree way forward | For Completion on a site by site basis
Assess options for procurement | Officer time | Corporate | Initiator | To be Agreed | Consider frameworks having assessd internal contract framework rules | For Completion on a site by site basis
Procure | Officer time | Corporate | Initiator | To be Agreed | Follow procurement process | For Completion on a site by site basis
Provide lead in cars | Officer Time | Corporate | Initiator | To be Agreed | Ensure efficient lead in cars secured. | As agreed with lease provider based on build times
Relet | Officer Time | Corporate | Initiator | To be Agreed | Lease cars proven to be a positive method of reducing mileage and payments and providing a safe and fit for purpose operational fleet. | As agreed. Typically 3 to 4 years from car delivery date
Improving Staff Information and Raising Awareness
Up to date Green Travel Plan | Officer time | Sustainability | Initiator | Bi Annual | An official review of the progress and update of the Travel Plan | For Completion on a site by site basis
Annual 'Travel to Work Week' | Officer Time | Sustainability | Initiator | Annually | Encourage staff to try other modes of travel now that personal car use is not required for business – particularly staff that live within 5 miles of Offices | Carried out with Café for free breakfast deal in 2015. No longer resources available.
Publicity Campaign | Officer Time | Sustainability | Initiator | 2017 | Official re-launch of Travel Action Plan key actions on Intranet to promote awareness. | Following completion of travel surveys
Car scheme FAQs, Trabvel Policy ,Travel Plan and Action Plan | Officer Time | Sustainability | Initiator | 2017 | Action Plan to be placed on Intranet for all staff and new starters. | Following acceptance by Cabinet/Board
Customer Information
Improved Information for Staff | Officer Time | Sustainability | Initiator | Ongoing | Install pictorial details in cars as to how to book, fuel, electrically charge, drive etc. FAQs revise on Intranet. Induction information of new starters supplied to HR. Super users signed up for EV charging advice and instruction. | Information reviewed annually or as significant changed are introduced.
Improved Customer Information | Officer Time | Sustainability | Initiator | Ongoing | Launch of Car Share to work map | Requires resources to relaunch
Promoting Car Sharing (commuting)
Encouragement of County Car Share / Lift Share | County funded | County Budgets | Initiator | On-going | Ongoing promotion and regular search for suitable matches | Promoted within surveys and as part of annual publicity campaigns
Guaranteed Ride Home Arrangement (for car sharers) | £Figure | Corporate Travel | Initiator | Ongoing and subject to 2 yearly review | Budget required to ensure guaranteed lift home after reasonable efforts have been made by officer/line manager to secure a free or low cost alternative (where officer has come to work via car share or public transport in the expectation that they would have been able to return using a similar mode). | Agreed by Cabinet
Encouragement of commuter car share | Potential saving | Corporate Travel | Initiator | Ongoing | Where more than one officer/member are travelling, an annual recognition should be made to the driver who achieves the highest amount of car sharing incidents. | Make better use of Facilities data a
Car Share bays | Officer Time | Property | Initiator | Ongoing | Encourage use linking to car share map | Following Surveys
Promoting Public Transport
Continue with Office Managed Oyster Cards | Potential saving – Officer time | Corporate Travel | Initiator and Divisional Admin | Ongoing | Cards to supplement journeys to London for meetings or conferences are now in place | Set up and managed by division
Promote Railway Travel Discount | Officer Time | Corporate Travel | Initiator | Ongoing | As part of car booking flowchart linked to hierarchy (telephone/conference call, public transport, car pool etc.) | Ensure Travel cards available for new starters
Promote Bus subsidy | £As agreed | Corporate Travel | Initiator | Ongoing | Reduced price bus travel on production of staff ID and Travel Card for any bus journey starting of finishing in County | For Completion on a site by site basis
Promote sustainable travel on websites and appropriate media | Officer time | Corporate Travel | Initiator | Ongoing | Suggestions for alternative travel forms made available with appropriate links | Resource required
Encourage take up of working at home where practical / feasible and not adversely impacting on service to customers | Officer Time | Corporate Travel | Initiator | Ongoing | Ensure all are aware of the possibility if interested and ensure corporate approach is enacted across all divisions to allow interested staff to partake of this option (except in cases where office cover is critical). Ensure recording and monitoring of this information through IT software | Successfully operating with very flexible flexi-hours.
Continuation of Cycle Loans/salary sacrifice | Small NI revenue stream | Corporate Travel | Initiator | Ongoing | Scheme remains popular with several users and continual use of cycle shelters. | Staff can sign up by visiting: www.cyclescheme.co.uk
National Initiatives
Government policy on Clean Air | Significant | Anticipated funded by central Government via bidding | Initiator | During plan 2017-19 | Local authorities will now “be expected to develop new and creative solutions to reduce emissions as quickly as possible, while avoiding undue impact on the motorist”. Relates to Council's 3 Air Quality Management Areas. | Would make a justifiable case for the renewable powered and battery back up Electric Vehicle (EV) charging hub discussed previously. Also lends credence to the proposal for on-street parking EV charging infrastructure (which we’re in discussion with County highways on). http://www.cleanenergynews.co.uk/news/transport/air-quality-plans-offer-modest-proposals-on-local-level-as-critics-decry-fa
Local issues such as - East West Rail and Oxford to Cambridge Expressway | Significant | Government | Initiator | 10-15 years | In 2012, the Government made a commitment to the East-West Rail line to address the current connectivity issues to the east and west by rail. | Watching Brief
HS2 | Significant | Government | Initiator | 15 Years | While seen as a key part of national infrastructure, High Speed 2 (HS2) contributes little if anything to the overall infrastructure needs of the area. Working with partners, the organisation will work to minimise the impacts of the project both during construction and operation. | To be incorporated in the Local Plan following the projects receipt of Royal Assent.
Implement Station Plans (integrating public transport) at district wide rail stations | Officer Time | County Budget | Initiator | As Relevant | Work on-going and lead by County, Netwrk Rail and Train Operating Companies. | Discussions ongoing with Network Rail and TOCs. Requires resources to move forward.
Flexible and Home Working
Continue Hot Desking and more defined WfH activity | Unknown | Corporate | Initiator | Ongoing | Results in more flexible working patterns and likely increase in home working and reduced staff commuting. | Hot desking and desk reduction by XX% established by project team.
Connected Knowledge Strategy | Ongoing | Corporate | Initiator | Ongoing | Provides staff with the ability to work from any location, particularly from home. With expectation to reduce journeys.
Travel Avoidance Virtual Meetings
Video, web, audio conferencing | Unknown (part of Gateway offices project) | HR/IT | Initiator | Ongoing | Encourage use and dispel myths surrounding of these systems – several of which are already in place at the Gateway office. Take-up has been limited. | New technology is available within certain meeting rooms but needs to be more comprehensively promoted and training given in order to better mainstream its usage. Potential is enhanced following removal of incentives to drive.
Management and Monitoring
Utilise postcode database to establish and help link up Organisation's drivers and potential passengers for car share purposes. | Officer Time | Corporate | Initiator | 2017 | Permit accurate and manageable access to DVLA CO2 emissions data and approximate home locator (part of postcode) to provide details for commuting. | On-going. Requires resourcing.
Record licence data from DVLA | Officer Time and cost per enquiry | Finance/Payroll | Initiator | Ongoing | Car scheme requires staff to provide drivers licence to line manager for check and sign off. this has now been superseded by electronic checks to DVLA carried out by enterprise | New method removed cost, saves time and leads to new staff being granted access to cars much more efficiently.
Maintain and enhance work with Land and Air Quality Team to ensure joined up policies | Officer Time | Sustainability | Initiator | 2017 | Explore merit of combining Air Quality strategy with Carbon Management Strategy to improve efficiency and effectiveness. | Follows Government's Air Quality Plan launched in May 2017 which places actions to achive results with local authorities.
Following Travel plan action link directly to AQ action Plan:
|  | Air Quality | Initiator |  | 1. Electric car charging points;
2. Travel Plan effectiveness;
Urban Traffic Management System (UTMC) = sustainable travel
Establish Travel Reporting and Budget Information | Officer Time | Sustainability | Initiator | Annually | Important if Council wish to reduce mileage | Will require resourcing
Encourage Efficient Driving Techniques | Officer Time | Health and Safety Budgets |  | 2017 | To raise awareness of simple steps to reduce fuel use, tyre, brake and engine wear | Driving simulator or Driver Eco Training. Requires resourcing to move this forward.
Achieve ‘channel shift’ – move from face to face to technological communications. | Officer time |  |  | On going | Council are already starting to see the impact of channel shift though and despite the poor economic growth and an increase in demand for services face to face visits fell by 7% in 2010/11 | For Completion on a site by site basis
Redevelopment of website to enable residents to transact with us more easily. | Ca £3,000 and Officer time | Project Aspire Budget |  | Complete 2016 | Based on analysis of what people are doing on the site, updating the navigation to ensure that the most popular pages are easier to find | For Completion on a site by site basis
It should be noted that whilst the majority of resource implications set out above are for officer time. Officer time carries with it a cost and results in work in other areas being delayed.