## Overview
Stakeholder Engagement Matrix
Stakeholder Engagement Schematic
This schematic indicates the scope of stakeholders who should be kept involved or informed in the process of reducing grey fleet. This template can be adapted for organisational use and is a useful tool for planning stakeholder engagment at the outset and as a tracking tool during a project.
Benefit Matrix
The Benefit Matrix shows examples of stakeholders who may be involved in the process of tackling grey fleet and the different target issues which may engage them. This matrix is useful for targeting your communication and messaging to different stakeholders. This should be treated as a guide as stakeholders, target issues and reactions will vary between organisations.

## Stakeholder EngagementSchematic
Stakeholder Engagement Schematic
This schematic provides an overview of stakeholders who should be involved in the process of reducing grey fleet. It is a useful tool for planning stakeholder engagment at the outset and as a tracking tool during a project.
| Champion/Project Lead | Cabinet Member | Env’t Portfolio Holder | Sponsor | CEO | Finance Director | Finance department | Human Resources Mgr | Payroll Manager | H&S Officer | Sustainability Officer | Fleet manager | Procurement Manager | Legal Officer | Union Representative | Employee Representative | Communications Team | Middle Manager | Individual Officer | Exclusion groups | Public (Opinion) | Local business | Solution providers
Establish problem(s)
Establish baseline
Establish a Champion/Lead
On Board sponsor
Seek out natural allies
Set up working group
Consider all solutions
Meet with differnet groups
Set out Value at Stake
Establish +ves and -ves of change
Spell out benefits to stakeholders
Establish red lines
Assess and granularise data
Establish / Firm up potential savings (Journey assess)
Communicate
Develop business case/plan
Sound out key stakeholders
Are we complying with legislation and contracts?
Talk to Board
Talk to Leader (Councils)
Achieve agreement
Produce Action Plan
Communicate plan
Establish Travel Hierarchy
Soft market test
Agree minutae issues (EV, colour, make, model etc)
Agree Decals
Assess options to procure
Prepare ITT Docs
Procure
Question all tender providers
Ensure hierarchy is optimised
Award contract
Communicate
Set launch date
Prepare all final aspects
Ensure resources available for launch period
Set up/train superuser/champions group
Ensure all aspects finalised (e.g. fuelling)
Launch
Monitor
Tackle ASB
Communicate
Repeat last 3!

## Benefit Matrix
Benefit Matrix
The Benefit Matrix shows examples of stakeholders who may be involved in the process of tackling grey fleet and the different target issues which may engage them. This matrix is useful for targeting your communication and messaging to different stakeholders.
| Cost Savings | Consultancy income | Redundancies Delayed | Reduced CO2 Emissions | Reduced NOx (Air Quality) | Fewer Trips, Higher productivity | Reduced Congestion | Risk Reduction | Organisational Reputation/Leadership | Uniformity and Fairness | Mileage Reduced | Alternative Travel options considered | Claims process simplified | License, Vehicle, MOT checks simplified
Cabinet Member
Env’t Portfolio Holder
CEO
Finance Director
Human Resources Mgr
Payroll Manager
Procurement Manager
Legal Officer
Union Representative
Employee Representative
Middle Manager
Individual Officer
Public Opinion
Local Business
Legend:
Red: | Unimportant
Amber: | Of Interest
Green: | Motivator
White: | Not relevant